# 3rd PERC Executive Committee

# Brussels, 16 March 2009

# Agenda Item 4:  PERC Progress Report 2008-2009:

# The Executive Committee is requested to note the attached report, with its attachments.

- PERC progress report

- The period from the 2nd PERC Executive Committee to the 3rd Executive Committee has been the first real and full cycle of operation of the structure on its own logic and policy. During that time considerable progress has been made in the organisational development and the activities of PERC, as well as shaping its profile and positioning itself in the European trade union context. As the process will continue in the future, along with the achievements important experience was gained also from certain setbacks and engagements in complicated, multi-actor initiatives. These have been taken into account in the preparation of the PERC work programme for 2009 – 2010.

- Structural and functional development

- PERC is in the final stage of its internal structuring. Most of the basic structures are in place and have started activities.  These include:

- The Summer School, a forum for discussion and capacity building for the leadership level of member organisations, which took place for the first time in Budapest (1-3 September 2008). Most important – the discussions marked the first clear rebalancing of focus of the East – West dynamics of relations in PERC through recognising common problems in different forms across all Europe;

- The Women’s Committee, which held its inaugural meeting in Turin on 29-30 October 2008 and its first (planning) meeting on 25 February 2009. The activities of the Committee will build on the work of the ITUC CEE/NIS Womens’ Network and work in close cooperation with it and the ITUC and ETUC Women’s’ Committees;

- Preparations for the launching of the PERC Youth Committee in 2009 are almost completed; and,

- The PERC website and newsletter, which have been in operation since May 2008 ;

- Development of ad-hoc and temporary mechanisms to work on specific topics is underway.  These include task forces and networks on migration, organising, energy, trade union legal expertise, education and training. First meetings have been held to outline perspective for PERC angle of involvement and complimenting on-going policies and activities in ITUC and ETUC.

- Country-specific meetings (on Belarus and Uzbekistan) have revealed considerable potential for coordinated approaches among the relevant organisations. These bring together ITUC, PERC, ETUC, GUFs, affiliates and SSOs to build and focus policy orientation, define the roles of the partners involved and provide the basis for coherent and effective action;

- Regional policy discussions (Baltics and South Eastern Europe, February 2009) called for by the pressure of the financial and economic crisis and the need of trade unions for an efficient response to the effects.

- Cooperation with Baltic Sea Trade Union Network (BASTUN) has been intensified and management of the South-Eastern Europe Trade Union Forum has been successfully transferred to the region.  Important steps towards self-reliance and sustainability of the SEE Forum have been made with members taking more and more real ownership of the operation.

- As the annual cycle of PERC activities develops, there are encouraging signs that the work is increasingly responding to the challenges of the member organisations, due in large measure to their active involvement in planning and implementation of programmes and projects.  Further efforts need to be invested in this approach, as well as integrating issues, ideas and proposals from the international level in national trade union agendas.

- New projects and project proposals are being structured in a flexible way, to encourage two-way exchange of information and higher levels of input from the implementing organisations.  More attention will also be paid to ensuring appropriate levels of own-contribution by implementing organisations to the running of projects. Regional offices have been crucial to implementation to a number of key projects, and efforts will need to be made to maintain this important function in light of anticipated constraints on resources and staffing.

- Securing smooth operation of the regional offices is crucial for the efficiency of PERC operations. This calls for special attention and urgent support in 2009 – 2010 to their financial base, first of all the office in Sarajevo facing serious troubles already in the second half of 2009.

- Promotion of the World Day for Decent Work was an important feature of PERC activities this year.  PERC affiliates were particularly active in organising national events, and the secretariat provided advisory, technical and in some cases material support for these activities.

- Assistance was also provided to organisations facing serious structural and political challenges and requiring support to develop their responses and approaches to challenges on the ground, including in Georgia, Kosovo and Bosnia and Herzegovina,.  This support involved “training by doing” activities primarily focused on legal issues and policy development.

- Raising transparency and predictability the PERC work plan provides a framework for facilitating cooperation with SSOs, ILO/ACTRAV and other closely cooperating and supporting partners such as the FES.  Special meetings with these organisations are being held on the basis of the work plan to help ensure cohesion, improve effectiveness and avoid duplication of effort.  In some specific cases, such as Uzbekistan and the Balkans, contacts with NGOs have also been established to exchange information and examine possible cooperation.

# Interaction with international and European institutions and trade union structures

- PERC activities, particularly in Eastern Europe, have continued to focus on cooperation with the ILO in supporting the development of tripartite social processes and dialogue, legal frameworks and collective bargaining, including in Belarus, Georgia and Bulgaria.  Emphasis is being placed on building national trade union capacity on the application of ILO standards and instruments of the Council of Europe.

- PERC interaction with the European Union has focused especially on the issues of EU enlargement and the EU’s “Neighbourhood Policy”.  High level meetings have been held with the relevant European Commission Directorates-General, along with ongoing contacts with EU officials.  The response of the EU has been encouraging and positive, and these contacts are expected to expand and deepen.  Concerning other areas of EU policies and activities, cooperation with the ETUC is well established, and representatives from PERC affiliates from non-EU member states have been invited to part in ETUC delegations, working group meetings on sustainability and energy, and on migration.

- Cooperation with GUFs and European Industry Federations has also moved forward to different extent, with exchange of information, proposals for cooperation, joint initiatives and projects under development with the IUF, ICEM, IFBWW, ETUF-TCL (textiles), EPSU (public sector) and EMF (metals).

Quantitative and operational aspects of implementation

- The implementation rate of the 2008-2009 PERC programme, without the regional offices’ own activities:

|  | Status of implementation | Number of actions |
| --- | --- | --- |
| 1. | Planned and implemented | 75 |
| 2. | Not planned and implemented | 8 |
| 3. | Launched and continuing | 10 |
|  | TOTAL implemented | 93 |
| 4. | Planned and not implemented – dropped out/no financing | 10 |

17. Items had been dropped  because of changed conditions and priorities for organisations that have proposed them, e.g. Russian trade unions and the workshop on atypical forms of employment. Lack of financing was the other reason for dropping some items.

17. Activities aimed at project proposals have been implemented as far as PERC own capacity allows and need to be taken over by professional implementing agencies in the field of action for final shaping of proposals and submitting them to EU programmes.

18. In terms of dynamics the rate of implementation implies around 9 events a month only from the plan. These have been completed along with all other engagements of PERC staff with major external events:

  - Events of more structured nature - ILO annual conference, 8th European regional conference of the ILO (Lisbon, February 2009), ITUC survey on violation of trade union rights, maintaining relations with EU institutions, etc.

  - reactions to emerging challenges on the ground – now triggered by the pressure of the financial and economic crisis and specific country situations, e.g. Belarus, Georgia, Kosovo, etc.

19. The overall amount of work done outlines the potential of PERC for practical implementation of activities. In this sense the experiment with the “very ambitious” first PERC programme as “one off” exercise has been useful identifying “core” issue and challenging some traditional trade union assumptions. Inevitably it has come at the cost of overburdening of the staff and in some cases have dented the technical/organisational aspects of the service (linked to travel, accommodation). No important failures have been recorded.

20. Obviously in the future workloads need to be rebalanced to avoid endangering the quality and adequacy of reactions in terms of political aspects and relevance to real life challenges. This is to be taken into account in making the plan for 2009-2010.

| I. ACTIVITIES IMPLEMENTED AS PLANNED IN 2008-2009 |
| --- |
|  | Priority Area - Activities | Time | Venue | Financing |
| 1. | PERC EVENTS AND INTERNAL STRUCTURING |
| 1.1. | PERC Executive Committee meeting | 16 March 2009 | Brussels | PERC |
| 1.2. | PERC leaders visit to Russian and Ukrainian trade union organisations | 11-14 February 2008 | Moscow/ Kiev | PERC/FNPR |
| 1.3. | 2 meetings of PERC Presidency | June;Sept 2008 | Brussels | PERC |
| 1.4. | PERC Summer School | 1-3 September 2008 | Budapest | ILO ACTRAV/CGSLB/ PERC |
| 1.5 | Meeting of PERC women’s committee transitional body | 26 June 2008 | Brussels | PERC |
| 1.6. | Founding conference – PERC Women’s Committee | 30-31 October 2008 | Turin | PERC/CSC/ ITC |
| 1.7. | PERC Youth Committee Transitional structure meeting | 9 April 2008 | Brussels | PERC |
| 1.8. | PERC Migration Group meeting | 16-17 February 2009 | Brussels | FES |
| 1.9. | PERC Organising/Recruiting Group meeting | 29-30 May 2008 | Brussels | PERC//LO-DK |
| 1.10. | Workshop/meeting of PERC regional offices/ETUI-REHS Education/Ruskin College | 2-4 July 2008 | Ruskin college, Oxford | PERC/ETUI/Ruskin College |
| 1.11. | Starting and maintaining a monthly newsletter | On-going | Brussels | PERC |
| 1.12 | Starting and maintaining a PERC Website | On-going | Brussels | PERC |
| 1.13. | Support for ITUC WDDW | On-going to 7 October | Brussels | PERC/ITUC SF |
| 1.14. | Translation of documents | On-going | Brussels | PERC |
| 1.15. | Visit/Lecture of PERC president in Austria | 20-25 April | Vienna | FNPR |
| 1.16. | 2 regular meetings of SEE Trade Union Forum | 16-17 May 2008 29-30 Sept. 2008 | Sarajevo Zagreb | FES- Belgrade/own contribution/PERC |
| 2. | ORGANISATIONAL DEVELOPMENT AND CAPACITY BUILDING |
| 2.1. | Labour law, labour relations, social dialogue |
| 2.1.1. | Annual workshop of SEE legal network: Flexicurity and new developments of EU labour law | 29-30 September 2008 | Zagreb | ETUI/SDC |
| 2.1.2. | SEE Regional Workshop on the instruments of the European Social Charter (ESC) | 22-23 May 2008 | Banja Luka | 3 Belgian confederations?/ LO Norway? |
| 2.1.3. | PERC follow-up conference on ESC for NMS and NIS states and Russia: Right to Strike and Patterns of Industrial Action | 15-17 December 2008 | Bucharest | CSC |
| 2.1.4. | NIS regional workshop: Labour Dispute Resolution and the Right to Strike | 2-3 December 2008 | Moscow | PERC/ITUC-SF/LO-TCO |
| 2.1.5. | Regional workshop for Caucasus: Social dialogue in Europe | 5-7 November 2008 | Tbilisi | FES |
| 2.1.6. | Support for ILO and national trade union projects | On-going | PERC area |  |
| 2.2. | Trade union structural adjustment, recruiting members and efficient management |
| 2.2.1. | SEE regional workshop on organising/recruiting | 18-19 October 2008 | Banja Luka | LO-TCO |
| 2.2.2. | Baltic trade unions capacity building | 6-7 March | Parmu | EU-LO-TCO project |
| 2.2.3. | SEZ workshop in Kaliningrad | 8-9 July 2008 | Kaliningrad | FES |
| 2.2.4. | Nordic-Baltic programme on MNCs - evaluation | 23-24 October 2008 | Druskininkai | EU-LO-TCO project |
| 2.2.5. | Support for projects in organising/recruiting – e.g. ETUF-TCL project for SEE TCL sector, etc. | On-going | PERC area |  |
| 2.3. | Trade unions and the informalisation of labour and economic relations |
| 2.3.1. | Informal economy round table | 5-8 February | Yerevan | FNV |
| 2.3.2. | Informal economy round table | 25-27 February | Baku | FNV |
| 2.3.3. | Informal economy round table | 17-18 June 2008 | Podgorica | FNV |
| 2.3.4. | Informal economy round table | 25-27 April 2008 | Bishkek | FNV |
| 2.3.5. | IE national working group meeting | 18 march 2008 | Tirana | FNV |
| 2.3.6. | IE Advisory group meeting | 23 June 2008 | Brussels | FNV |
| 2.3.7. | IE regional workshop | 24-25 June 2008 | Brussels | FNV |
| 2.3.8. | Support for IE local activities |  |  |  |
| 2.4. | Trade union policies for reforming social protection system |
| 2.4.1. | Preparing special issue of SEER on health reform in SEE | 2008 | Brussels/Sarajevo | ETUI |
| 2.5. | Gender equality policy |
| 2.5.1. | Women seminar on organising in Nordic companies in the Baltics | 26-27 March 2008 | Jurmala | EU-LO-TCO project |
| 2.5.2. | ILO/PERC project on discrimination of women in the workplace in CEE and NIS | 2008 – on-going |  | Flemish government/ Belgian unions |
| 2.5.3. | 9th Women School | 27-29 October 2008 | Turin | Flemish government/Belgian unions/ICT/ILO ACTRAV ??? |
| 2.5.4. | Women’s Network regional conference c CEE and NIS | 29 October 2008 | Turin | Flemish government/Belgian unions/ICT/ILO ACTRAV ??? |
| 2.5.5. | Decent work – decent life for women | 12-13 February | Kotor | LO-TCO |
| 2.5.6. | Workshop Gender Aspects in New General Collective Agreement of Montenegro | 27 November | Montenegro | LO-TCO |
| 2.5.7. | Workshop Building the capacities of women in trade unions | 11-12 January | Belgrade | LO-TCO |
| 2.6. | Youth policy |
| 2.6.1. | Mapping out of youth representation in PERC organisations | 2008 – on-going | Brussels | PERC/ETUI |
| 2.6.2. | Baltic workshop for youth organising | 30 June-4 July 2008 | Palanga | EU-LO-TCO project |
| 2.6.3. | PERC youth summer camp | 30 June-4 July 2008 | Palanga | FES/FNPR |
| 2.6.4. | SEE regional youth workshops | 11-12 February 08 and 22-23 January | Sarajevo Kotor | LO-TCO |
| 2.6.5. | Demographic changes in Europe (CoE) | 8-14 September 2008 | Strasburg | CoE/ETUI |
| 2.6.6. | Ukraine youth project conference | 13-14 May 2008 | Kiev | EU-SDA project |
| 2.7. | Public relations and communications strategies of trade unions |
| 2.7.1. | Preparing a project in that area for NIS and SEE organisations | On-going | Brussels | PERC |
| 2.8. | Child labour |
| 2.8.1. | PERC support for the Global March Against child labour conference | 19-20 May 2008 | Moscow | FNPR, ILO |
| 2.8.2. | PERC support for the Global March Against child labour conference | 16-18 September 2008 | Sofia | FNPR/ PERC/ILO |
| 2.8.3. | Workshop on child labour in Kirgizstan | 16-17 July 208 | Bishkek | ILO |
| 3. | MIGRATION |
| 3.1. | Setting up PERC task force on migration | 16-17February 2009 | Brussels | FES |
| 3.2. | Mapping out available approaches and instruments in inter-union cooperation | On-going | Brussels | PERC |
| 3.3 | GSEE/ITUC/PERC conference on trafficking and forced labour | 21-23 Novemeber 2008 | Athens | GSEE, ITUC-SF |
| 3.4. | Support for ITUC/ETUC activities on migration ad trafficking of people | On-going | Brussels |  |
| 4. | ENERGY |
| 4.1. | Participation of NIS energy experts in ETUC energy group meeting | 15-16 September | Brussels | PERC/ITUC-SF |
| 4.2. | NIS regional policy meeting: Trade Unions and Energy Policy development in Europe | 22-23 October | Kiev | FES |
| 5. | EDUCATION AND TRAINING |
| 5.1. | SEE regional workshop: EU-IPA assistance instrument and project development skills for trade union activities. | 14-15 May 2008 | Brussels | ETUI/SDC |
| 5.2. | Gender policy course with Ruskin College | 3-7 March 2008 | Oxford | Ruskin College / ITUC-SF |
| 5.3. | Support for leadership in democracy course | June 2008 | Oxford | Ruskin College |
| 5.4. | ETUE follow-up |  | Belgrade | ILO/LO-TCO |
| 5.5. | ETUE follow-up |  | Tirana | ILO/LO-TCO |
| 5.6. | ETUE strategic workshop |  | Tirana | ILO/LO-TCO |
| 5.7. | Training courses in Russia |  | Moscow/ St. Petersburg | FNPR |
| 5.8. | ETUE in Lithuania | On-going | Vilnius | ILO |
| 5.9. | Workshop for NIS trade union educators | 16-27 February 2009 | Turin | ITC |
| 6. | SUPPORT FOR ORGANISATIONS IN SPECIAL CONDITIONS |
| 6.1. | Belarus country meeting | 9 July 2008 | Brussels | PERC/LO-TCO |
| 6.2. | Campaign against Labour Code in Georgia – expert training | 19-21 May 2008 | Brussels | CGSLB |
| 6.3. | Campaign against Labour Code in Georgia | On-going | Tbilisi/Brussels | PERC |
| 6.4. | Training of BSPK legal experts in preparation of labour laws | 20-22 October 2008 | Brussels | PERC/ITUC-SF |
| 6.5. | Supporting BSPK in the process of preparing a package of laws in labour and social laws. | 2008 - ongoing | Pristina - Brussels |  |
| 6.5. | Seminar: BiH ratification of ESC | 21-23 May 2008 | Banja Luka | CSC/FGTB |
| 6.6. | Kaliningrad – strengthening industry unions | On-going | Kaliningrad | LO-DK/STTK |
| II. NON-PLANNED, ADDITIONAL ACTIVITIES IMPLEMENTED IN 2008-2009 |
| 1. | SEE Regional Workshop: Social clauses in IFIs lending strategies | 5-6 May 2008 | Sofia | FES |
| 2. | NIS Regional Workshop: Social clauses in IFIs lending strategies | 12-13 November 2008 | Baku | PERC/ITUC-SF/ILO |
| 3. | Policy discussion meeting on the crisis in the Baltics | 6 February 2009 | Brussels | PERC/ITUC-SF |
| 4. | Extraordinary meeting of SEE Trade Union Forum on the economic crisis | 27-28 February 2009 | Podgorica | FES- Belgrade/own contribution/PERC/LO-TCO |
| 5. | Extraordinary meeting of PERC Women’s Committee | 25 February 2009 | Brussels | PERC |
| 6. | Support 2 additional meetings of the ETUF-TCL on organising | September 2008 November 2008 | Podgorica Bled | ETUI/PERC |
| 7. | Uzbekistan country meeting | 24 Sept. 2008 | Brussels | ITUC/PERC |
| 8. | Seminar on gender mainstreaming: gender audit in the sphere of social partnership | 2-5 June | Kiev | FNPR/FPU/PERC |
| III. PLANNED ACTIVITIES LAUNCHED AND PARTIALLY IMPLEMENTED/CONTINUING IN 2008-2009 |
|  | Priority Area - Activities | Time | Venue | Reason |
| 1 | PERC leaders visit to Caucasus region | 5-6 November 2009 | Tbilisi | Changed conditions after the war. Replaced by Deputy General Secretaries (ITUC/ETUC) |
| 2 | Transferring South East European Review into a PERC region quarterly | Launched and continuing | Brussels/ Moscow | ETUI strategy to publisher shaped |
| 3. | Preparation of long-term training project/s for SEE and NIS regions | Launched and continuing | Brussels | Problems with implementing agency |
| 4. | Gender mainstreaming in collective bargaining | 2-3 April 2009 | Tashkent | Delayed by local decision-making procedures. FES funding. |
| 5. | ETUE in Ukraine | Launched and on-going | Kiev | Pending on trade union developments |
| 6. | Study visit for legal experts from NIS and Russia: Complimentarity and use of ILO-CoE instruments for protection of labour and trade union rights | June/July | ICTurin/ Strasburg | Delayed for setting up ITUC Labour rights network/ No financing |
| 7. | ETUE follow-up: BiH |  |  | Pending on development of KSBiH |
| 8. | ETUE follow-up: Montenegro |  |  | Pending, subject to CTUM readiness |
| 9. | Virtual Labour Academy project – concept frame and project outline ready | Preparation launched and on-going |  | Delayed by problems with implementing partners |
| 10. | Advancing OSH in Ukrainian mining – concept frame and project outline ready | On-going |  | Searching for implementing agency. |
| IV. PLANNED ACTIVITIES NOT IMPLEMENTED IN 2008-2009 |
| 1. | NIS Regional Conference New Forms of Employment | May-June 2008 | Moscow | Not relevant in changing conditions. Cancelled by affiliates. |
| 2. | Assisting FPKg |  |  | Not relevant. FPKg not ITUC /PERC member |
| 3. | ETUE in Bulgaria |  |  | Subject to further discussions |
| 4. | Research on ethnic based employment |  |  | No financing |
| 5. | SEE regional workshop for developing of trade union structures | Spring 2008 | Belgrade | No financing |
| 6. | NIS regional workshop on organising/recruiting |  |  | No financing |
| 7. | NIS workshop on pension systems reform |  |  | No financing |
| 8. | Developing SEE network on health reform |  |  | No financing |
| 9. | Developing PERC energy task force |  |  | No financing |
| 10. | Trade unions and energy policy – round table |  | Brussels | No financing |

| Activity Report 2008-2009 – Moscow office |
| --- |
| I. ACTIVITIES IMPLEMENTED AS PLANNED IN 2008-2009 |
|  | Priority Area - Activities | Time | Venue | Financing |
| 1. | PERC EVENTS AND INTERNAL STRUCTURING |
| 1.1. | Visit of General Secretary and Executive Secretary to Russian and Ukrainian affiliates | 11-14 Feb. 2008 | Moscow, Kiev | PERC |
| 2. | ORGANISATIONAL DEVELOPMENT AND CAPACITY BUILDING |
| 2.1. | Labour law, labour relations, social dialogue |
| 2.1.4. | PERC/ILO Regional Workshop ENP: Labour Dispute Resolution – labour courts, arbitration, conciliation | December | Moscow | PERC/ITUC-SF/LO-TCO |
| 2.1.5. | ITUC workshop on IFIs policies | November | Baku | ITUC-SF/ILO |
| 2.3. | Trade unions and the informalisation of labour and economic relations |
| 2.3.1. | Tripartite Round Table on Informal employment | April 2008 | Bishkek | FNV |
| 2.4. | Trade Union Policies for reforming social protection systems |
| 2.4.1 | Kaliningrad partners 3rd conference follow-up on special economic zones | July, 2008 | Kaliningrad | FES, LO-DK |
| 2.6. | Youth policy |
| 2.6.1. | Youth project in Ukraine: |  |  |  |
|  | Seminar on collective labour disputes | 12-14 March | Chernigov | EU-SDA |
|  | Train the trainer methodic seminar | 14-16 April | Kiev | EU-SDA |
|  | Evaluation conference | 12 – 14 May | Kiev | EU-SDA |
|  | Working groups | 12 – 14 April | Kiev | EU-SDA |
| 3. | MIGRATION |
| 3.1. | Support for ISCOS activities for regulated migration and against trafficking of people | 2008 | Ukraine Moldova | ISCOS |
| 4. | ENERGY |
| 4.1. | Trade Unions and Energy Policy Development in Europe – Round table | October 2008 | Kiev | FES |
| 6. | SUPPORT FOR ORGANISATIONS IN SPECIAL SITUATION |
| 6.1. | Belarus – TU approach for transformation policy implementation Follow-up seminar on privatization and restructuring | 25-26 Feb. 2008 | Minsk | Solidarity Center/ PERC |
| 6.2. | Assisting FPKG (Kyrgyzstan) and FPRK and CFTUK (Kazakhstan) preparing for ITUC/PERC membership |  | NIS | ITUC/LO-TCO |
| 6.3. | Kaliningrad – activities for strengthening TUs and industry organizations | 9-11 November | Kaliningrad | LO-DK; FES; IMF |
| II. NON-PLANNED, ADDITIONAL ACTIVITIES IMPLEMENTED IN 2008-2009 |
| 1. | Facilitation of FNV consultative workshop | February 2008 | Vilnius | FNV |
| 2. | Child labour round table in Moscow | May 2008 | Moscow | ILO/PERC/FNPR |
| 3. | ILO anti-discrimination workshop | June 2008 | Minsk | ILO/PERC |
| 4. | Support for country meeting on Belarus | 9 July 2008 | Brussels | PERC/LO-TCO |
| 5. | Child labour workshop | July 2008 | Bishkek | ACTRAV/ IUF |
| 6. | Participation in BASTUN meeting on mobility of labour | November 2008 | Copenhagen | PERC |
| III. PLANNED ACTIVITIES LAUNCHED AND PARTIALLY IMPLEMENTED/CONTINUING IN 2008-2009 |
| 1. | Campaign against forced short term contract labour, in Belarus, kick-off round table |  | Minsk | Postponed on political grounds |
| IV. PLANNED ACTIVITIES NOT IMPLEMENTED IN 2008-2009 |
| 1. | Training KVPU negotiators team for regional social dialog |  | Kiev, Ukraine | No financing |
| 2. | Organising seminar Russia | May 2008 – march 2009 | Russia | No financing |
| 3. | Organising seminar Russia Kazakhstan | May 2008 – march 2009 | Kazakhstan | Cancelled by partner organisation |
| 4. | Regional workshop on health reform - ENP |  |  | No financing |

| Activity Report 2008-2009 – Vilnius Office |
| --- |
| I. ACTIVITIES IMPLEMENTED AS PLANNED IN 2008-2009 |
|  | Activity | Time | Venue | Financing |
| 1. | FNV Informal Economy Project |
| 1.1. | National mapping reports | By April 2008 | Georgia, Serbia, Ukraine, Croatia | FNV |
| 1.2. | Summary report | June 2008 |  | FNV |
| 1.3. | Tripartite Round tables, workshop for women and youth | February 2008 | Azerbaijan, Armenia | FNV |
| 1.4. | Tripartite Round table, workshop for women and youth | April 2008 | Bishkek, Kyrgyzstan | FNV |
| 1.5. | National working group meeting | March 2008 | Tirana Albania | FNV |
| 1.6. | Tripartite Round table, workshop for women and youth | June 2008 | Montenegro | FNV |
| 1.7. | Advisory group meeting Regional thematic workshop SEE/NIS | June 2008 | Brussels Belgium | FNV |
| 1.8. | 1st circle countries national working group meetings, national seminars and campaigns | August-December 2008 | Serbia, Croatia, Ukraine, Georgia | FNV |
| 1.9. | 2nd circle national working groups | August 2008 – March 2009 | Azerbaijan Armenia, Montenegro Albania Kyrgyzstan | FNV |
| 1.10. | National mapping reports | By November 2008 | Azerbaijan, Armenia, Montenegro, Albania, Kyrgyzstan | FNV |
| 2. | LO-TCO-EU-Baltic project (LPSK, LDF, LPS”Solidarumas”, LBAS, EAKL, TALO) |
| 2.1. | Workers organizations capacity building seminar | 6-7 March 2008 | Parnu, Estonia | LO-TCO/EU |
| 2.2. | Women organizing in Nordic companies seminar | 26-27 March 2008 | Jurmala, Latvia | LO-TCO/EU |
| 2.3. | TU Young activists training on organising | 27June July 3 2008 | Palanga, Lithuania | LO-TCO/EU |
| 2.4. | IT Training for local shop stewards | 17-18 September 2008 | Riga, Latvia | LO-TCO/EU |
| 2.5. | Project working group meeting | 22 October 2008 | Druskininkai, Lithuania | LO-TCO/EU |
| 2.6. | Project evaluation conference | 23-24 October 2008 | Druskininkai Lithuania | LO-TCO/EU |
| 3. | LO Danmark Organising programme |
| 3.1. | Setting up PERC Task Force on organizing and recruiting: bringing together East and West operations and experience | 29-30 April 2008 | Brussels | PERC, LO-DK |
| 4. | Other sub-regional activity |
| 4.1. | Euroneman TU Network meeting | November 7-8 2008 | Kaliningrad | FES Warsaw |
| 4.2 | Euroneman TU Network Women meeting | October 11-12 | Grodno Belarus | FES Warsaw |
| 4.3 | BASTUN meeting | 18 March 2008 | Riga, Latvia | NFS |
| 4.4 | PERC Youth summer camp | June 26-2 July 2008 | Palanga Lithuania | FES PERC |
| 4.5 | BASTUN Investigation mission to Belarus | April 2008 | Belarus Minsk | BASTUN |
| 4.6 | FNPR education programme for neighboring organizations | April 2008 | Moscow Russia | FNPR |
| 4.7 | Meeting with Labour Friendly NGOs on IE questions | November 18-19 2008 | Warsaw Poland | FES |
| 4.8 | BASTUN Working group meeting | August 25 2008 | Vilnius Lithuania | BASTUN |
| 4.9 | Informal economy seminar | 17-18 December | Moldova, Kishinev | LO-TCO Sweden |
| 4.10 | Baltic Sea Labor Network working group meeting | 19 January 2009 | Stockholm Sweden | BSLN |
| 4.11 | BSLN Baltic meeting | February 3 | Riga Latvia | BSLN |
| 4.12 | Baltic region crisis meeting | February 6 | Brussels Belgium | PERC |
| 5. | Kaliningrad region |
| 5.1. | LO Denmark project Strategic planning seminar | April 2008 | Kaliningrad | LO Denmark |
| 5.2. | Kaliningrad partners 3rd conference | July 2008 | Kaliningrad | FES |
| 5.3. | 2 seminars with IF Metall Sweden and IMF Moscow | June 2008 | Kaliningrad | IF Metall |
| 6. | Co-operation with ILO |
| 6.1 | Seminar on Organizing for Romanian Hungarian Metal sector TU | April 16-17 2008 | Bucharest Romania | ILO Turin |
| 6.2 | Seminar on Organizing for Slovenian and Croatian Metal sector TU | June 13-14 2008 | Ljubljana Slovenia | ILO Turin |
| 6.3 | IE in construction sector project introducing seminar | August 27-28 2008 | Podgorica Montenegro | ILO Budapest |
| 6.4 | Project working meeting | January 26 2009 | Sarajevo Bosnia | ILO Budapest |
| 6.5 | IE Construction project seminar | February 19 | Albania Tirana | ILO Budapest |
| 6.6 | IE Workers organizations capacity building | December 11-12 | Bishkek Kyrgyzstan | ILO Moscow |
| IV. PLANNED ACTIVITIES NOT IMPLEMENTED IN 2008-2009 |
| 1. | 4 national trainings on organising | May 2008 –March 2009 | Kazakhstan, Russia, Romania, Serbia | No financing |

| Activity Report 2008-2009 – Sarajevo Office |
| --- |
| ACTIVITIES IMPLEMENTED AS PLANNED IN 2008-2009 |
|  | Priority Area - Activities | Time | Venue | Financing |
| 1. | PERC EVENTS AND INTERNAL STRUCTURING |
| 1.1. | SEE Trade Union Forum meeting | May 2008 | Sarajevo | FES and Lo Tco Done |
| 1.2. | SEE Trade Union Forum meeting | September 2008 | Zagreb | FES and Lo-Tco Done |
| 1.3. | Translation of information and analytical materials | ongoing |  | LO Norway, LO-TCO and PERC |
| 2. | ORGANISATIONAL DEVELOPMENT AND CAPACITY BUILDING |
| 2.1. | Labour law, labour relations, social dialogue |
| 2.1. | SEE regional workshop on the European Social Charter and Social Acquis Communitaire | May 2008 | Banjaluka | FGTB, ACLVB and ACV |
| 2.2. | National follow up workshop in Bosnia and Herzegovina | September 2008 | Brcko | FNV, LO-TCO, LO Norway |
| 2.3. | Organizational and expert support to the CGT antidiscrimination project in SEE | October 2008 | Paris | CGT |
| 2.4. | Organizational and expert support to the ILO ADA project on bipartite social dialogue and peaceful labor dispute settlement | ongoing | Budapest, BiH and Serbia, | ILO |
| 2.5. | Participation on the Netlex Conference | November 2008 | Brussels | ETUI-REHS |
| 2.2. | Trade Union structural adjustment, recruiting members and efficient management |  |  |  |
| 2.2.1 | Regional Workshop on organizing and recruiting members following PERC Task Force meeting | October 2008 | Banjaluka | LO-TCO |
| 2.2.2. | Targeted expert assistance to projects in filed and disseminate results – e.g. ETUF-TCL in SEE, LO-TCO on MNCs in SEE | On-going | Skopje, Istanbul, Podgorica Bled |  |
| 2.2.3 | Assisting consolidation and development processes of Trade Union organizations in Kosovo, BiH and others | September 2008 | Brussels | ITUC - SF |
| 2.3. | Trade unions and the informalisation of labour and economic relations |
| 2.3.1. | Planned activities for 2008 in a 3 – year PERC project on informal economy in Eastern Europe National Working group meetings National Working group meeting National Working Group meeting | March 2008 June 2008 February 2009 | Tirana Podgorica Tirana | FNV - PERC |
| 2.4. | Trade Union Policies for reforming social protection systems |
|  | Roundtable on pension system reforms in Republika Srpska (BIH) | February 2008 | Biljeljina | FNV and LO Norway |
| 2.5. | Women’s policy |  |  |  |
|  | SEE Women network conference – “Decent Work, Decent Life for Women” | February 2008 | Kotor | LO-TCO |
|  | Two national follow ups of the workshop on ILO 183 and decent work Decent Life campaign Follow up roundtable in Montenegro Follow up in Serbia | November 2008 January 2009 | Podgorica Belgrade | LO-TCO |
| 2.6. | Youth policy |
|  | Regional youth network Workshop – facilitating the setting up of the PERC YC and youth policies | February 2008 | Sarajevo | LO-TCO and LO Norway |
|  | 2 follow-up workshops: Decent Work-Decent Life Campaign | October and December 2008 | Podgorica | LO-TCO |
|  | Mapping of the SEE youth representation in PERC organisations | ongoing |  |  |
|  | Education and Training |  |  |  |
|  | Working meeting of core group of evaluators | March 2008 | Brussels | LO-TCO and ILO |
|  | Core team planning of the ETUE program | April | Budapest | ILO and LO-TCO |
|  | Preparation of the Guide on Evaluation of Trade Union Education | ongoing |  | ILO and LO-TCO |
|  | Follow up roundtable and Task force group meeting in Serbia with CATUS | December 2008 | Belgrade | ILO and LO-TCO |
|  | Strat5egic workshops with the BSPSH and KSSH in Albania | March 2008 | Tirana | ILO and LO-TCO |
|  | Follow up working group meetings with the KSSH and BSPSH | January 2009 | Tirana | ILO and LO-TCO |
| 6. | SUPPORT FOR ORGANISATIONS IN SPECIAL SITUATION |
| BiH | Training for Trainers: Gender equality at the working place | May 2008 | Sarajevo | FNV and LO-TCO |
| BiH | 5 one day seminars on gender equality at the working place | June 2008 | Brcko, Zavidovici, B. Gradiska and Sarajevo | FNV, LO-TCO, LO Norway |
| BiH | Youth forum seminar on “Decent work, decent life” | September 2008 | Banjaluka | FNV, LO-TCO |
| BiH | Trade union rights seminars with legal experts/educators 10 one-day seminars on occupational healthy and safety 1 seminar on Law on strike 1 seminar on Works Councils | April 2008 - February 2009 | Prijedor, Srebrenica, Kotor Varos, Jablanica, B. Gradiska, Derventa, Trebinje, Bijeljina, Vares, Tesanj, Teslic Sipovo, Konjic | FNV, LO Norway and LO-TCO |
| BiH | Consolidating professional federations Seminar with metal workers TUs | May and November 2008 | Kotor Varos and Zenica | FNV and LO Norway |
| BiH | Workshop with legal experts on the ELS (directives) | November 2008 | Ilidza | FNV |
| Kosovo | Roundtable on the labour legislation | June 2008 | Pristina | LO-TCO |
| II. NON-PLANNED, ADDITIONAL ACTIVITIES IMPLEMENTED IN 2008-2009 |
|  | Meeting between the SEE TU Forum coordinator and the RCC representatives | July 2008 | Sarajevo |  |
|  | Meeting between the SEE TU Forum representatives and the RCC representatives | November 2008 | Zagreb | PERC |
|  | SEE TU Forum extraordinary meeting on economic crises | February 2009 | Podgorica | FES and LO-TCO |
|  | Translation of the ITUC Guide on informal economy into B/H/S | May 2008 | Sarajevo | LO Norway |
|  | Cross-border meeting on informal economy with TU experts from Montenegro and Serbia | October 2008 | Belgrade | FNV - PERC |
|  | Assistance to the ILO project on “Strengthening Social Partnership in Western Balkans: Albania, Bosnia and Herzegovina and Montenegro” Sub regional seminar on informal economy in the construction sector Working group meeting on informal economy with the construction TUs | August 2008 February | Podgorica Tirana | ILO |
|  | Study visit: European Enlargement: Social Perspectives for the Western Balkans | May 2008 | Brussels | Solidar OPC |
|  | World day for decent work – 7 October roundtable | October 2008 | Doboj | ITUC |
|  | SEED Youth Gathering on World Day for Decent work | October 2008 | Bela Crkva | ITUC |
|  | Participation on the Solidar Balkan network meeting | November 2008 | Belgrade | LO-TCO |
|  | PERC SEE Youth workshop on “Decent work, Decent Life” and youth mapping | January 2009 | Kotor | Lo-TCO |
|  | Assistance to the UGT ISCOD project in Bosnia and Herzegovina and Serbia Project planning meeting Follow up planning meetings Follow up planning meeting | April 2008 May 2008 November 2008 | Madrid Belgrade and Sarajevo Sarajevo | ISCOD |
| III. PLANNED ACTIVITIES LAUNCHED AND PARTIALLY IMPLEMENTED/CONTINUING IN 2008-2009 |
|  | Consolidating the SEE TU expert group on health reform Preparation of special issue of SEER in local languages Meeting to prepare a regional conference on health reform | Budapest / PERC Summer school | September 2008 | PERC |
| IV. PLANNED ACTIVITIES NOT IMPLEMENTED IN 2008-2009 |
|  | Maintaining web-site of the SEE Trade Union Forum |  |  |  |
|  | National Trade Union conference for BiH ratification of the European social Charter | postponed |  | LO Norway and FNV |
|  | Trade union rights national trainings (Macedonia, Albania, Montenegro or Serbia) | Not realized |  |  |
|  | SEE Regional workshop: Trade Union structures, organizational integrity and efficient social dialogue | postponed |  | FES |
|  | 2 national follow-up activities on organizing in SEE | Not realized |  |  |
|  | Consolidating the SEE T expert group on pension reform - meeting of the experts | postponed |  |  |
|  | 1 Full ETUE process in Croatia on the Evaluation of TU education | Shifted to 2009 |  | ILO and LO-TCO |
|  | Follow up activities on the Evaluation of TU education in Montenegro and Bosnia and Herzegovina | No interest for the activities |  |  |