# 2nd EC/PERC/5 – Appendix III

# PERC Vilnius Office - Work plan 2008

|  | Activity | Time | Venue | Financing | Partners Experts |
| --- | --- | --- | --- | --- | --- |
| 1. | FNV IE Project | A. Leppik Office Vilnius |
| 1.1. | National mapping reports | By April | Georgia, Serbia, Ukraine, Croatia | FNV | K. Petkov |
| 1.2. | Summary report | April |  | FNV | K. Petkov |
| 1.3. | Tripartite Round tables, workshop for women and youth | February | Azerbaijan, Armenia | FNV |  |
| 1.4. | Tripartite Round table, workshop for women and youth | April 2008 | Biskek, Kyrgyzstan | FNV | A.Mrost ILO Moscow? |
| 1.5. | National working group meeting | April 2008 ? | Tirana Albania | FNV | J.Redzepovic |
| 1.6. | Tripartite Round table, workshop for women and youth | May 2008? | Montenegro | FNV | J.Redzepovic |
| 1.7. | Advisory group meeting Regional thematic workshop SEE/NIS | June/May 2008 | Brussels Belgium | FNV | PERC, IUF, BWI, UNI, FNV |
| 1.8. | 1st circle countries national working group meetings, national seminars and campaigns | August-December 2008 | Serbia, Croatia, Ukraina, Georgia | FNV | A.Mrost J.Redzepovic |
| 1.9. | 2nd circle national working groups | August December 2008 | Azerbaijan Armenia, Montenegro Albania? | FNV | A.Mrost J.Redzepovic L.Messman |
| 1.10. | National mapping reports | By November | Azerbaijan, Armenia, Montenegro, Albania, Kyrgyzstan | FNV | K. Petkov |
| 1.11. | Updating summary report | April |  | FNV | K. Petkov |
| 2. | LOTCO-EU-Baltic project (LPSK, LDF, LPS”Solidarumas”, LBAS, EAKL, TALO) | Office Vilnius |
| 2.1. | Workers organizations capacity building seminar | 6-7 March 2008 | Parnu, Estonia | LO-TCO/EU | LO Norway ETUC? |
| 2.2. | Women organizing in Nordic companies seminar | 26-27 March 2008 | Jurmala, Latvia | LO-TCO/EU | LO Sweden Olga Nicolae |
| 2.3. | TU Young activists training on organising | June 2008 | Palanga, Lithuania | LO-TCO/EU | PERC ETUC? Baltic TU Youth Forum |
| 2.4. | IT Training for local shop stewards | September 2008 | Riga, Latvia | LO-TCO/EU | Lo Denmark |
| 2.5. | Project working group meeting | 22 October 2008 | Druskininkai, Lithuania | LO-TCO/EU |  |
| 2.6. | Project evaluation conference | 23-24 October 2008 | Druskininkai Lithuania | LO-TCO/EU | G.Gradev L.Issakson A.Leppik |
| 3. | LO Danmark Organising programme (if confirmed) | Office Vilnius |
| 3.1. | Setting up PERC Task Force on organizing and recruiting: bringing together East and West operations and experience | 29-30 May 2008 | Brussels | PERC, LO-DK? |  |
| 3.1. | 4 national trainings | May 2008 –March 2009 | Kazakhstan, Russia, Romania Serbia | Lo Denmark | A.Mrost |
| 4. | Other sub-regional activity | Office Vilnius |
| 4.1. | Euroneman TU Network meeting | October 2008 | Kaliningrad | FES Warsaw | C.Rode |
| 4.2. | BASTUN meeting | 18 March 2008 | Riga Latvia | NFS | G.Gradev |
| 4.3. | PERC Youth summer camp | June 26-2 July 2008 | Palanga Lithuania | FES PERC | ???? |
| 5. | Kaliningrad region | Office Vilnius |
| 5.1. | LO Denmark project First meeting | April 2008 | Kaliningrad | LO Denmark | A.Mrost J. Ohrt |
| 5.2. | Kaliningrad partners 3rd conference | July 2008 | Kaliningrad | FES | DGB, Lo-Danmark, ILO Moscow, GUFs |
| 5.3. | 2 seminars with IF Metall Sweden and IMF Moscow | Spring-summer 2008 | Kaliningrad | IF Metall | V. Borisov IUF A. Mrost IF Metall Sweden |